## Sheet1
TASKS | Assign to | Due Date | Done | Estimation (hs) | Duration (hs)
Create project | Roberta | 2019-07-17 | ok
Create tasks in the project | Roberta | 2019-07-19 | ok
Write integration tests (at least 5 test cases using the Selenium Web Driver and Nunit and Firefox as your Web client) | Chinmay | 2019-07-27 |  | 5
Write 3 acceptance tests | Chinmay
Insert car/owner information | Dmytro
Displaying the previously-entered contact and vehicle information | Dmytro
Validate information in JavaScript | Dmytro | 2019-07-24 | ok
hyperlink to JD Power and Associates | Dmytro
Displaying a list of previously saved data | Dmytro
Account page HTML | Thao | 2019-07-22 | ok | 1 | 1
Home page HTML | Thao | 2019-07-28 |  | 1
Account and car page CSS | Thao | 2019-07-22 | ok | 1 | 2
Home and cars page CSS | Thao | 2019-07-28 |  | 2
High level design doc (1/2 page) | Roberta | 2019-07-25 | ok | 0,5 | 0,25
Detailed design doc | Roberta | 2019-07-30
Dev tasks (Name of the dev - Due Dates - Estimation) | Roberta | 2019-07-26
Testing (Name of tester - Dates - Estimation) | Roberta | 2019-07-26
Screenshot of Git repository commits | Roberta | 2019-08-05
Use cases | Roberta | 2019-07-29 | ok | 2 | 1
activity diagram | Chinmay/Roberta | 2019-07-25 | ok | 1 | 1
Do the system Integration (Selenium + Pages) | Chinmay
Execute Integration tests (Selenium) | Chinmay